## Sprint1
|  |  |  | Week #1 (12 hrs / week) | [6 empty] | Week #2 (12 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 30 x 3) | Day1 | Day2 | Day3 | Day4 | Day5 | Day6 | Day7 | Day8 | Day9 | Day10 | Day11 | Day12 | Day13 | Day14
|  |  |  | 2022-02-26 | 2022-02-27 | 2022-02-28 | 2022-03-01 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-05 | 2022-03-06 | 2022-03-07 | 2022-03-08 | 2022-03-09 | 2022-03-10 | 2022-03-11
|  |  |  | 240 | 231 | 222 | 213 | 204 | 195 | 186 | 177 | 168 | 159 | 150 | 141 | 132 | 123 | Ideal hours
|  |  | 90 | 162 | 159 | 152 | 131 | 115 | 99 | 92 | 78 | 60 | 50 | 33 |  |  |  | Remaining Hours
Architecture diagram | Architecture diagram | Nithin/Prasad | 10 | 0 | 0 | 2 | 2 | 1 | 0 | 0 | 2 | 2 | 0 | 1 | 0 | 0 | 0
DB design | DB design | Samrudh/Nithin | 12 | 0 | 0 | 1 | 3 | 0 | 2 | 0 | 2 | 0 | 2 | 2 | 0 | 0 | 0
Frontend baseline | Frontend baseline | Samrudh | 10 | 0 | 0 | 8 | 0 | 3 | 0 | 1 | 0 | 0 | 2 | 3 | 0 | 3 | 0
Backend baseline | Backend baseline | Nithin | 14 | 0 | 0 | 4 | 3 | 0 | 0 | 3 | 4 | 4 | 3 | 0 | 0 | 0 | 0
Wireframes | Wireframes | Prasad | 8 | 0 | 0 | 0 | 1 | 4 | 0 | 2 | 2 | 0 | 1 | 2 | 0 | 0 | 0
Unit Testing Framework | Unit Testing Framework | Samrudh | 6 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0
UI routing protection added | UI routing protection added | Prasad | 10 | 0 | 0 | 2 | 0 | 2 | 1 | 0 | 2 | 0 | 2 | 1 | 0 | 0 | 0
UML Diagrams | UML Diagrams | Nithin | 10 | 0 | 2 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 3 | 3 | 0 | 0 | 2
|  |  | Total | 90 | 90 | 73 | 63 | 52 | 48 | 42 | 30 | 23 | 12 | 2 | -15 | -27 | -34
|  |  | Ideal | 72 | 67 | 62 | 57 | 52 | 47 | 42 | 36 | 30 | 24 | 18 | 12 | 6 | 0
Team:
Varun | 9 hours / Week
Sakshi | 9 hours / Week
Raj | 9 hours / Week
Shivani | 9 hours / Week
Total Available Hours During Sprint: | 72

## Sprint2
|  |  |  | Week #1 (12 hrs / week) | [6 empty] | Week #2 (12 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 18 x 4) | Day1 | Day2 | Day3 | Day4 | Day5 | Day6 | Day7 | Day8 | Day9 | Day10 | Day11 | Day12 | Day13 | Day14
|  |  |  | 2022-03-12 | ##### | 2022-03-14 | 2022-03-15 | 2022-03-16 | 2022-03-17 | 2022-03-18 | 2022-03-19 | 2022-03-20 | 2022-03-21 | 2022-03-22 | 2022-03-23 | 2022-03-24 | 2022-03-25
|  |  |  | 240 | 231 | 222 | 213 | 204 | 195 | 186 | 177 | 168 | 159 | 150 | 141 | 132 | 123
|  |  | 72 | 72 | 68 | 62 | 54 | 47 | 41 | 38 | 35 | 32 | 27.5 | 19
Faculty Courses UI | Design UI to display list of Published courses | Samrudh | 8 | 0 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 2 | 1.5 | 1 | 0 | 0 | 0
Faculty Course Content API | Create fetch course content. | Nithin | 12 | 2 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 2 | 0
Faculty Courses API | Develop backend to fetch Faculty courses | Prasad | 10 | 0 | 0 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 3 | 0
Faculty Courses API | Integrate frontend and backend for Faculty courses | Prasad | 6 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0
Faculty Courses UI | Design UI to display list of Unpublished courses | Samrudh | 8 | 0 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0
Student Courses API | Create fetch enrolled courses content. | Prasad | 6 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0
Student Courses API | Integrate frontend and backend for Student courses | Nithin | 6 | 1 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0
Student Courses UI | Design UI to display list of enrolled courses | Samrudh | 10 | 0 | 0 | 1 | 2 | 3 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 0 | 0
Student Course Content API | Backend for course content | Nithin | 6 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0
|  |  | Total | 68 | 62 | 54 | 47 | 41 | 38 | 35 | 32 | 27 | 19 | 11 | 8 | 2 | 0
|  |  | Ideal | 72 | 67 | 62 | 57 | 52 | 47 | 42 | 36 | 30 | 24 | 18 | 12 | 6 | 0
Team:
Varun | 9 hours / Week
Sakshi | 9 hours / Week
Raj | 9 hours / Week
Shivani | 9 hours / Week
Total Available Hours During Sprint: | 72

## Sprint3
|  |  |  | Week #1 (12 hrs / week) | [6 empty] | Week #2 (12 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 18 x 4) | Day1 | Day2 | Day3 | Day4 | Day5 | Day6 | Day7 | Day8 | Day9 | Day10 | Day11 | Day12 | Day13 | Day14
|  |  |  | 2022-03-26 | ##### | 2022-03-28 | 2022-03-29 | 2022-03-30 | 2022-03-31 | 2022-04-01 | 2022-04-02 | 2022-04-03 | 2022-04-04 | 2022-04-05 | 2022-04-06 | 2022-04-07 | 2022-04-08
|  |  |  | 240 | 231 | 222 | 213 | 204 | 195 | 186 | 177 | 168 | 159 | 150 | 141 | 132 | 123
|  |  | 72 | 71 | 66 | 52 | 34 | 23 | 19 | 11 | 5 | -5 | -12 | -30 | 8 | 5 | 5
Faculty Syllabus Content API | Create API to add syllabus content | Prasad | 8 | 0 | 3 | 2 | 2 | 0 | 0 | 1 | 2 | 4 | 4 | 0 | 1 | 2 | 2
Faculty Syllabus Content UI | Design UI for Faculty to input syllabus content | Samrudh | 10 | 3 | 2 | 3 | 1 | 2 | 0 | 2 | 0 | 1 | 3 | 3 | 1 | 2 | 2
Faculty View Student List API | Create API to fetch student lists for courses | Nithin | 8 | 0 | 2 | 3 | 3 | 2 | 4 | 2 | 4 | 1 | 3 | 3 | 1 | 0 | 0
Faculty Assignments and Quizzes UI | Design UI for Faculty to input assignment and quiz details | Samrudh | 8 | 1 | 0 | 5 | 1 | 0 | 1 | 1 | 2 | 0 | 4 | 1 | 0 | 1 | 0
Faculty View Grades API | Create API to fetch student grades | Nithin | 12 | 0 | 2 | 3 | 1 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 0 | 0 | 0
Faculty Syllabus Content API | Integrate frontend and backend for syllabus content | Prasad | 8 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0
Faculty Assignments and Quizzes API | Create API to add assignments and quizzes | Prasad | 10 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0
Faculty Assignments and Quizzes API | Integrate frontend and backend for assignments and quizzes | Nithin | 8 | 2 | 4 | 2 | 0 | 0 | 3 | 0 | 2 | 0 | 1 | 0 | 2 | 0 | 1
|  |  | Total | 65 | 53 | 34 | 23 | 19 | 11 | 5 | -5 | -12 | -30 | -41 | -49 | -54 | -59
|  |  | Ideal | 72 | 67 | 62 | 57 | 52 | 47 | 42 | 36 | 30 | 24 | 18 | 12 | 6 | 0
Team:
Varun | 9 hours / Week
Sakshi | 9 hours / Week
Raj | 9 hours / Week
Shivani | 9 hours / Week
Total Available Hours During Sprint: | 72

## Sprint4
|  |  |  | Week #1 (12 hrs / week) | [6 empty] | Week #2 (12 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 18 x 4) | Day1 | Day2 | Day3 | Day4 | Day5 | Day6 | Day7 | Day8 | Day9 | Day10 | Day11 | Day12 | Day13 | Day14
|  |  |  | 2022-04-09 | ##### | 2022-04-11 | 2022-04-12 | 2022-04-13 | 2022-04-14 | 2022-04-15 | 2022-04-16 | 2022-04-17 | 2022-04-18 | 2022-04-19 | 2022-04-20 | 2022-04-21 | 2022-04-22
|  |  |  | 240 | 231 | 222 | 213 | 204 | 195 | 186 | 177 | 168 | 159 | 150 | 141 | 132 | 123
|  |  | 72 | 72 | 64 | 57 | 42 | 32 | 23 | 20 | 16 | 10 | 3 | -4
Admin View Courses API | Create API to fetch courses by Faculty | Nithin | 8 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 2 | 1 | 2 | 0 | 0 | 0
Faculty View Grades UI | Design UI to display grades for each student. | Samrudh | 6 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
Faculty Assign Grades | Create API to assign grades to students | Prasad | 8 | 0 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Admin View Courses API | Create API to fetch courses by Semester | Nithin | 4 | 3 | 0 | 2 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0
Faculty Assign Grades | Integrate frontend and backend for assigning grades | Prasad | 8 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0
Student Profile and Notifications | Create API for setting profile information and managing notifications. | Prasad | 6 | 0 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
Admin Assign Course API | Create API to assign courses to Faculty | Nithin | 6 | 2 | 2 | 0 | 2 | 0 | 0 | 0 | 3 | 0 | 3 | 3 | 0 | 0 | 0
Student View Grades UI | Design UI to display student grades | Samrudh | 10 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 2 | 2 | 2
Student Profile and Notifications | Integrate frontend and backend for profile information and notifications | Prasad | 12 | 1 | 0 | 3 | 0 | 2 | 1 | 0 | 2 | 1 | 2 | 0 | 1 | 0 | 0
Student Profile and Notifications UI | Design UI for inputting profile information | Samrudh | 6 | 2 | 0 | 1 | 2 | 1 | 0 | 2 | 0 | 1 | 0 | 1 | 0 | 1 | 0
Student Profile and Notifications UI | Design UI for inputting Setting Notification Preferences | Samrudh | 4 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
|  |  | Total | 64 | 57 | 42 | 32 | 23 | 20 | 16 | 10 | 3 | -4 | -11 | -16 | -20 | -23
|  |  | Ideal | 72 | 67 | 62 | 57 | 52 | 47 | 42 | 36 | 30 | 24 | 18 | 12 | 6 | 0
Team:
Varun | 9 hours / Week
Sakshi | 9 hours / Week
Raj | 9 hours / Week
Shivani | 9 hours / Week
Total Available Hours During Sprint: | 72

## Sprint5
|  |  |  | Week #1 (12 hrs / week) | [6 empty] | Week #2 (12 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 18 x 4) | Day1 | Day2 | Day3 | Day4 | Day5 | Day6 | Day7 | Day8 | Day9 | Day10 | Day11 | Day12 | Day13 | Day14
|  |  |  | 2022-04-23 | ##### | 2022-04-25 | 2022-04-26 | 2022-04-27 | 2022-04-28 | 2022-04-29 | 2022-04-30 | 2022-05-01 | 2022-05-02 | 2022-05-03 | 2022-05-04 | 2022-05-05 | 2022-05-06
|  |  |  | 240 | 231 | 222 | 213 | 204 | 195 | 186 | 177 | 168 | 159 | 150 | 141 | 132 | 123
|  |  | 72 | 72 | 63 | 54 | 46 | 39 | 35 | 31 | 27 | 18 | 7 | 0
Faculty Announcements UI | Design UI for Faculty to post and view announcements | Samrudh | 6 | 3 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0
Faculty Announcements API | Create API to post announcements | Prasad | 10 | 0 | 3 | 0 | 2 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
Student View Announcements UI | Design UI for Students to view announcements | Samrudh | 6 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0
Faculty Announcements API | Integrate frontend and backend for announcements | Nithin | 10 | 0 | 1 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Final Deployment | Deploy APIs and database to AWS | Samrudh/Nithin/Prasad | 8 | 0 | 2 | 0 | 1 | 2 | 2 | 1 | 3 | 1 | 1 | 0 | 0 | 0 | 0
Final Deployment | Ensuring auto-scaling and load balancing | Samrudh/Nithin/Prasad | 8 | 2 | 1.5 | 2 | 1 | 0 | 0 | 2 | 3 | 1 | 1 | 2 | 1 | 2 | 0
Testing and Validation | Ensure all APIs and frontend functionalities work as expected | Samrudh/Nithin/Prasad | 20 | 2 | 1.5 | 4 | 1 | 0 | 2 | 0 | 2 | 3 | 2 | 1 | 1 | 1 | 2
|  |  | Total | 63 | 54 | 46 | 39 | 35 | 31 | 27 | 18 | 7 | 0 | -5 | -2 | -5 | -7
|  |  | Ideal | 72 | 67 | 62 | 57 | 52 | 47 | 42 | 36 | 30 | 24 | 18 | 12 | 6 | 0
Team:
Varun | 9 hours / Week
Sakshi | 9 hours / Week
Raj | 9 hours / Week
Shivani | 9 hours / Week
Total Available Hours During Sprint: | 72